## Sheet1
Color | Status | TASK | WEEK 9.03-15.03 | WEEK 16.03-22.03 | WEEK 23.03-29.03 | WEEK 30.03-05.04 | WEEK 06.04-12.04
| Done | Create project idea | Maryna Hordiienko
| In progress | Create GitHub repository | Maryna Hordiienko
|  | Add project description to README | Maryna Hordiienko
STAGE-1 / Planning / UX tasks
Maryna Hordiienko
Aleksy Cieslak |  | Project Concept and Problem Statement | Maryna Hordiienko
|  | Define Target Users | Maryna Hordiienko/Aleksy Cieslak
|  | Create User Persona 1 | Maryna Hordiienko
|  | Create User Persona 2 | Aleksy Cieslak
|  | Create User Flow / Task Journey |  | Maryna Hordiienko/Aleksy Cieslak
|  | Create Low-Fidelity Wireframes | Aleksy Cieslak | Aleksy Cieslak
|  | Define Project Scope |  | Maryna Hordiienko
|  | Export Planning Document to PDF |  | Maryna Hordiienko
|  | Add planning PDF to Git repository |  | Maryna Hordiienko
STAGE-2 /
|  | Create database and migrations |  | Maryna Hordiienko |  | Maryna Hordiienko
|  | Visual Appearance / CSS |  |  |  |  | Maryna Hordiienko/Aleksy Cieslak
|  | Implement authentication |  |  |  |  | Maryna Hordiienko
|  | Create Task model |  | Aleksy Cieslak |  | Aleksy Cieslak
|  | Implement CRUD for tasks |  | Aleksy Cieslak
|  | Create Blade views |  | Aleksy Cieslak |  | Aleksy Cieslak
|  | Add client-side validation |  |  |  |  | Maryna Hordiienko
|  | Add server-side validation |  |  |  |  | Maryna Hordiienko
|  | Create Home Page |  |  |  |  | Maryna Hordiienko
Test application